Tier-1 Operations CAS TOR -  18 July 2008

# Service Name

#### CASTOR

## Summary of week gone:

- Completed testing of 2.1.7-10

  - Tested developers fix for Cupv mult-domain problem

- Diskservers for cms and atlas put into puppet

  - Gridmap file updates every 4 hours on these

- All hardware/OS for RAC systems complete

- Continue upgrade of tape servers to 64-bit; 5 old 32-bit tape servers decommissioned

- Investigated problems with lhcb disk2disk copy

## Developments

- Testing of 2.1.7-11 as soon as available – expected at end of week

- Move lhcb diskservers into puppet

- Work on resolving xrootd problems for alice

- Reinstitute preprod system for testing means of replicating atlas conditions data.

  - Could we use any Tier1 diskservers?

- Work on diskserver deployment workflows

- Use decommissioned tapeservers to build 64-bit SRMs

- Work on changes/additions to nagios tests

- Work on additional puppet hosts for redundancy, test, and development; also web report of puppet hosts

- Atlas dcache migration; expect completion by 31 Aug

- Atlas plan for service classes for new diskervers

### Operational Issues and Incidents

| Not in Use (need number scheme?) | Description | Start | End | Severity | VOs Affected |
| --- | --- | --- | --- | --- | --- |
|  | Lhcb pending jobs rising rapidly | 16 July 10:20 | 16 July 12:30 | Stopped lhcb instance; SAM failure | lhcb |
|  | Atlas stager database slowdown | 15 July 16:20 | 16 July 14:20 | All atlas response very slow; SAM failure | atlas |

## Summary of plans for week ahead:

### Scheduled and Cancelled Down Times:

#### Type=Down/At Risk/Cancelled entriesin/planned to go to GOCDB

| Component | Description | Start | End | Type |
| --- | --- | --- | --- | --- |
| Lhcb diskservers | Install puppet | Tue 10:00 | Tue 16:00 | At-risk |
| Cms and lhcb instances | Upgrade to 2.1.7 | 22 Jul & 23 Jul |  | Canceled for this week |

#### No other planned changes in production

### Development priorities:

Key work in progress areas:

- Test 2.1.7-11 as soon as available

- Get xrootd working

- Puppet for lhcb servers

- 64-bit SRM install

- Preprod system

### Advanced Warning of Requirements and Blocking issues:

- Potential problems with delay of  castor 2.1.7-11 release; may not be able to complete upgrade by 11 Aug if any further delays of critical staff shortage due to holidays

- Will need to upgrade to new Cupv before upgrading stagers to 2.1.7 and will need to modify all Cupv entries to use FQDN.  Need to review this with CERN and plan for it.

- Need additional (old?) diskservers for testing atlas conditions data configuration.

Planned schedule through August:

28 Jul-1 Aug	Test 2.1.7-11

29 Jul 		Migrate atlas stager, atlas srm, lhcb stager, lhcb srm onto Neptune RAC

4 Aug 		Cms instance, 2.1.7-11

5 Aug  		Gen instance, 2.1.7-11

6 Aug  		Atlas instance, 2.1.7-11

7 Aug 		Lhcb instance, 2.1.7-11

8 Aug+	Castor client on batch farm and UIs, 2.1.7-11

11 Aug  	Migrate nameserver, cms stager, cms SRM, gen stager, gen SRM onto Pluto RAC;

install cms and gen DLF

11 Aug  	Bring up atlas and lhcb DLF services on Neptune RAC; brief stager downtime